## Sprint1
Sprint 1 Backlog
Task | Assigned Team Member |  | Time Used/Left (hrs) | [11 empty] | Totals
|  | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12
Revise the initial product backlog | Jingru Ruan | 2 | 1.75
Setup the initial Sprint 1 backlog and update backlog | Jingru Ruan | 4 | 0 | 2.5 | 1
Create Burndown Chart | Jingru Ruan | 2
User Story 1(SF-1)
Create UML diagram | Jingru Ruan
Tile queue populated with five random values from 0 - 9
9x9 game board populated with 49 random values from 0-9 arranged in 7x7 grid
Start immediately after launching app
start after previous game, timed or untimed, completed
User Story 2(SF-3)
Only first tile from the tile queue may be selected
Place onto corner tile of game board
Place onto border tile of game board
Can only place onto unoccupied tile of game board
User Story 3(SF-4)
First tile of tile queue(the one selected) must be removed, remaining tiles moved up one position, new tile added in last position
User Story 4(SF-5)
Tile must appear in square selected
Unoccupied neighboring squares contribute 0 to the sum
If the sum of the three neighboring tiles modulo is equal to the number on the placed tile, the neighboring tiles and the placed tile must be removed.
User Story 5(SF-8)
Number of moves left must be 50 when game is started
Number of moves must decrease by 1 each time a tile is placed
User Story 6(SF-11)
user is able to view the accumulated points while playing the game
User Story 7(SF-12)
Can only be done once
Totals